## Sheet1
MMJ Tracking Sheet |  | 2017-02-08
Priority 1 | March Issue (March 15, 2017)
Priority 2 | June Issue (June 15, 2017)
Priority 3 | September Issue (September 15)
Priority 4 | December Issue (December 15, 2017)
Long term | 2018
[5 empty] | Completion Date |  | Notes
STRATEGIC AREAS OF APPROACH |  | Status | Priority | Team Owner | Projected | Actual
INFRASTRUCTURE
Journal Handbook | Document job descriptions and responsibilities of editorial board, associate editors, reviewers, staff. | In progress | 4 | All | end March 2017 | 2017-04-01
| Include contracts, both blank and current | In progress | 4 | Lucinda | end March 2017 | 2017-04-01
| Develop a journal budget for current year and projected for next year | In progress | 4 | Lucinda | end March 2017 | 2017-04-01
| Develop and include sample reports: For the Editorial Board and AJPP | In progress | 4 | Lucinda | end March 2017 | 2017-04-01
| Include author and reviewer documents, including workflow (process documentation) | In progress | 4 | All | end March 2017 | 2017-04-01
Journal Sustainability
Transition to Gold Open Access | Project a journal budget withh APC and related expenses to visualize the transition and determine feasibility | In progress |  | Lucinda | 2017-03-01
| Ensure transfer of MMJ financial account to the College | In progress | 2 | Lucinda | 2017-04-01
| Consider posed issues and discuss at AJPP May meeting | In progress | 2 | Lucinda | end February 2017 | Mid-March 2017
Print Edition | Review decision on print subscriptions (and consider 1 print version for the year, prepaid to allow for print on-demand) | In progress | 1 | Lucinda | end February 2017 | Mid-March 2017
| Explore alternate printing of limited number of issues for distribution to paid subscribers of the print and to district hospitals | In progress |  | Lucinda | 2017-07-01 | 2017-07-01
| OA: Journal needs to identify itself as such, with model info, on website | Done |  |  | Immediately | end February 2017
Advisory Board | Create a journal advisory board and post members on website | In progress | 1 | Lucinda | Immediately | end February 2017
| Send sample letter of invitation to join an advisory board | Done |  | CBC
| Consider asking other EiCs to join Adv Bd |  |  |  | Immediately | on-going
Revenue generation | Explore other revenue generating opportunities (ads in print and digital ads) | In progress |  | Lucinda | Immediately | on-going
CONTENT
New Content | Developing new content types and sections on the website | In progress |  | Andrew
· Profiles in Leadership (aka A Deeper Look)
· News
· Resource Center (info on legalizing abortion)
Online First | Determine what content will be online first and then define it (in journal documentation and on website) | In progress | 1 | Andrew | 2017-02-17 | 2017-02-17
| Possible to start with corrected proofs of papers scheduled for the March issue or June special issue and any accepted manuscripts | In progress | 1 | Andrew | 2017-02-17 | 2017-02-17
| If agreed upon, content curator to identify list of 3-5 for inclusion on home page; will need to update this list as status of the article changes | In progress | 1 | Andrew | 2017-02-17 | 2017-02-17
Conference Abstracts | Identify the abstract issues published | To do | 1 | Thengo | 2017-11-10 | 5th Dec
| Identify the topics of the abstract issue (check the conference program) and start with DEC 2016 | To do | 1 | Thengo | 2017-11-10 | 5th-Dec
| Create separate page on the site to list and promote these | To do | 1 | Thengo | 2017-02-01 | 24th Feb
Special Issues | Identify the special issues published | To do | 1 | Thengo | 2017-05-01 | 30th August
| Identify the topics of the special issue | To do | 1 | Thengo | 2017-05-01 | 30th August
| Create separate page on the site to list and promote the special issues, both published and to come | To do | 1 | Thengo | 2017-02-01 | 2017-02-24
Key Words | Agree on set of keywords and begin application | In progress | 1 | Andrew and Lucinda | Immediately | end February 2017
| See other sections on implementation: aims and scope, author instructions, ScholarOne set up and author communications, application of categories and tags to articles |  | 1
Back Issues | Compile back issues and convert to complete archive | To do | 2 | CBC
| Determine back date, 2000? | To do | 2 | CBC
| Gather sources of content (digital and hard copy) | To do | 2 | CBC
| Ensure completion of data (e.g., Vol/Issue, DOI, etc.) | To do | 2 | CBC
| Calculate number of articles | To do | 2 | CBC
| Determine source of the conversion (SPI for an additional fee) and then delivery | To do | 2 | CBC
| Check if Elsevier would offer the conversion gratis | In progress | 1 | CBC
Citation and Indexing | Contact Bioline to see if they can take the XML file provided by SPI | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Contact Sabinet to see if they can take the XML file provided by SPI | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Ask SPI to send a test sample of the XML file from the June 2016 issue, which can be used to coordinate this file type delivery to Bioline and Sabinet | To do | 1 | Thengo | 2017-01-30 | 2017-02-05
| Based on discussions with Sabinet, obtain necessary XML files to update their holdings | To do | 1 | Thengo | 2017-02-01 | 2017-03-01
| Complete the Scopus documentation to become “owner” and “deliverer” of the MMJ content | To do | 1 | Thengo | 2017-02-01 | 2017-02-03
| Set up Scopus accounts for Lucinda and Andrew | Done |  | CBC
| Provide contact info for Scopus demo for Andrew | Done |  | CBC
| Check on how to submit XML to Google: through webmaster account? | To do | 1 | Andrew (and Joel) | 2017-02-24
JOURNAL ARTICLE PROCESS
Document Process | Review draft flowchart to ensure understanding and expectation, plus definition of responsibilities | In progress | 2 | Thengo and Andrew
| Determine where to post the approved process documents: journal handbook, author info, etc. | To do | 2 | Andrew
Schedule | Review draft publication schedule for MARCH issue | In progress | 1 | Thengo and Andrew | 2017-02-10 | 2017-02-25 | Andrew to send all accepted manuscripts to Thengo by 1-Feb-17
| Revise and then complete schedule for 2017 issues | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Keep track of actual dates to inform efficiencies in future scheduling | To do | 1 | Thengo | 2017-02-01 | 2017-02-25
Style Guide | Agree on a style guide (which can be used in the MSS Editing) | In progress | 2 | Andrew
| Determine where to post | To do | 2 | Andrew
| Update author instructions to include reference to this guide | To do | 2 | Andrew
Author Instructions | Review in general and update | To do | 2 | Team with next PWB volunteer
| Create a document to show authors how to insert their corrections in the PDF | Would be nice | 2 | Andrew
| Add instruction to include keywords | To do | 1 | Andrew | 2017-02-24 | 2017-02-24 | Needs to be updated with new keywords once finalised
| Add instruction to have authors suggest reviewers | To do | 1 | Andrew | 2017-02-24 | 2017-02-24
| Add request to have authors link to journal article on MMJ site once published | To do | 1 | Andrew | 2017-02-24 | 2017-02-24
| Add request to have authors connect to journal social media pages | To do | 1 | Andrew | 2017-02-24 | 2017-02-24
Author Submission (ScholarOne) | Configure submission site to allow for: | To do | 1 | Andrew | 2017-02-03 | 2017-02-03
| Authors to suggest reviewers for their paper | To do | 1 | Andrew | 2017-02-03 | 2017-02-03
| Authors to add keywords | To do | 1 | Andrew | Done | Done
| Add request to have authors link to journal article on MMJ site once published | To do | 1 | Andrew | 2017-02-24 | 2017-02-24
| Add request to have authors connect to journal social media pages | To do | 1 | Andrew | 2017-02-24 | 2017-02-24
| Update author letters to reflect changes | To do | 1 | Andrew | 2017-03-03 | 2017-03-03
WEBSITE
Design and Layout | Review design and layout and how to update to accommodate new decisions on content, improve/enhance engagement, etc. | Done | 1
| Webmaster review | Done | 1
| Webmaster work to implement changes | In progress | 1 | Joel
| Provide webmaster with all curated content to populate new elements | To do | 1 | Thengo and Andrew | 2017-02-01 | 2017-02-15
| Development site available for review | To do | 1 | All + CBC | 2017-02-01 | 2017-02-15
| Revise and determine go live date (MARCH) | In progress | 1 | All | 2017-03-15
| Advise Editorial Board of site changes (approval not required) and have it go with email update on PWB work | To do | 1 | Lucinda
| Primary contact with webmaster | NA |  | Thengo | 2017-02-01 | 2017-02-25
Navigation | Agree on suggested navigational changes | In progress | 1 | Thengo and Andrew | 2017-02-01 | 2017-02-15
| Ensure webmaster has this info to apply to the new site | In progress | 1 | Thengo | 2017-02-01 | 2017-02-15
| Ensure all new pages are created on the site to match new navigation | To do | 1 | Joel
About (Ancillary) Pages | These are information pages on the site, not part of the issue dataset |  | 1
About Us | Create a separate page for Aims and Scope, incorporating high level key words as high level topics within journal scope. Add the journal Impact Factor on this page. | To do | 1 | Lucinda | Immediately | end February 2017
| Make Mission Statement own page | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Create an abstracting and Indexing page for the MMJ | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Provide a sample Abstracting and Indexing page | To do | 1 | CBC
| Update the MMJ history and make own page | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Develop Info for Advertisers and post as own page: available placement options, ad sizes accepted, fees, etc. | In progress | 1 | Thengo | 2017-02-01 | 2017-02-15
AJPP | Add a new page about AJPP and tells the story of MMJ connection, which links to AJPP, and which identifies the other AJPP journal partners | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Update AJPP page to reflect new editor and include link to her interview | In progress | 1 | Andrew | 2017-03-03
Staff | Separate page for journal staff | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Identify key responsibilities for staff for more direct contact and inquiries | To be determined | 1 | All
| Add Joel Kumwenda as journal webmaster | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Ensure staff have connected back to MMJ from their other pages (social media, linked in, university or institution profile) | In progress | 1 | Thengo and Andrew | 2017-02-01 | 2017-02-15
Editorial Board | Update Editorial Board with more individual information: photo, add'l credentials, areas of specialty, institution and country | To do | 1 | Lucinda
| Staff to contact Ed Bd members to solicit the above information | To do | 1 | Lucinda
| Staff to contact Ed Bd members to ask them to link back to the journal from their social media pages, LinkedIn profile and/or institutional profile page | To do | 1 | Lucinda
Abstracting and Indexing | Add new page that lists where MMJ is indexed: PubMed, PubMed Central, AJOL, Scopus, Bioline, Sabinet |  | 1
Author Instructions | See above for details |  | 1
For Reviewers | Agree on revised reviewer completion form and then post to the site | In progress | 1 | Andrew | 2017-02-03 | 2017-02-03
| Add a reviewer's toolkit: How to Review a Paper | To do | 2 | Andrew
| Extract 2016 reviewer information from ScholarOne (name, institution, country) plus ask Ed Bd if hey have used reviewers outside the system | To do | 1 | Andrew | 2017-02-05 | 2017-02-05
| Post 2016 reviewer info as separate page on website (Reviewer Appreciation or Acknowledging Our Reviewers), including short description and words of thanks | To do | 1 | Thengo | 2017-02-24 | 2017-02-24
Journal Club | Determine how Journal Club will be integrated into journal site: navigation, own page, listing of articles discussed at club and facilitators, more on Facebook page | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
Issue Table of Contents | Add topic headings to organize articles. These would replicate the high level keywords and topics within journal scope. | To do | 1 | Andrew
| Determine when this can be implemented (MARCH?) | To do | 1 | Andrew | 2017-02-01 | 2017-02-15
Article Pages | Add DOI to the HTML version of article | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Use keywords as categories and tags at the article level in WordPress | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Reposition Facebook and Twitter icons to each article to encourage sharing | To do | 1 | Thengo
| Identify articles by their type (e.g., original research) and high level topic | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
| Include author keywords in both PDF and HTML versions of the article | To do | 1 | Thengo
Home Page Updates | Identify home page content curator | Done |  | Andrew | 2017-02-01 | 2017-02-15
| Identify deadline for home page updates to production | Part of agreed upon production schedule |  |  | 2017-02-01 | 2017-02-15
| Provide both the small and large container info for the MARCH issue: legalization of abortion topic | In progress | 1 | Andrew with Fanuel and Mphatso
| Identify the Issue Highlight articles and thumbnail image and identify by topic and article type | To do | 1 | Andrew
Abortion Topic | Determine the content for the small and large containers | In progress | 1 | Andrew with Fanuel and Mphatso | 2017-02-09
| Edit the interview (overview) document to pull out quotes or teaser text and then the final version for large container posting | In progress | 1 | Andrew with Fanuel and Mphatso | 2017-01-29
| Edit the "expert opinion" pieces and determine what will be published (abstract now with full paper later?), get author photo and use that plus teaser for larger container display | In progress | 1 | Andrew with Fanuel and Mphatso | 2017-02-05
| Identify related articles from the MMJ archive and create list for larger container | In progress | 1 | Andrew with Fanuel and Mphatso | 2017-02-09
| identify any news related links | In progress | 1 | Andrew with Fanuel and Mphatso | 2017-02-09
| Determine how to promote this special content on social media | In progress | 1 | Andrew with Fanuel and Mphatso | Ongoing
Conference Abstracts | Identify content listing for the Conference Abstracts tab | To do | 1 | Thengo | 2017-02-01 | 2017-02-25
| Create a new page for Conference Abstacts and list all issues that fit this content category (fits under new nav item, Articles and Issues) in chronological order (newest to oldest). More info about the most recent abstracts, with links to specific conference topics | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
Special Issues | Determine how to use the home page to promote and identify the Special Issue | To do | 1 | Andrew | 2017-02-17
| Consider calling these "Themed Issues" | To do | 1 | All
| Identify content listing for the Special Issues tab: This should be about the March NCD issue with a link to the new page that lists all special issues | To do | 1 | Andrew
| Create a new page for Special Issues and list all issues that fit this content category (fits under new nav item, Articles and Issues) in chronological order (newest to oldest). | To do | 1 | Thengo | 2017-02-01 | 2017-02-15
June Issue | Determine small content container for the home page and begin content gathering and curation | To do | 2 | Andrew
September Issue | Determine small content container for the home page and begin content gathering and curation | To be determined | 3 | All
| Interviews with researchers on campus? | To be determined | 3 | All
| Coordination with campus groups doing research to develop a "feed" so MMJ can connect them with MMJ community | To be determined | 3 | All
| Coordination with campus groups to identify critical recent research to include on site (list of articles/links, Malawi Research by our Partners, e.g.) | To be determined | 3 | All
| Search MMJ archive to find most relevant research by Malawians and create a Related Articles list | To be determined | 3 | All
See Word document on ideas for the SEPT issue
Search | Move the current search box to be positioned above the RH column (which appears on home page and all article pages) NOTE: Not sure makes sense to move out of nav bar so team will need to explore options and see what works | To be determined | 1 | Thengo, Andrew and Joel | 2017-02-09
| Add Google Search widget if possible | To do | 1 | Joel
Search Results | Explore how to ensure articles are identified by date (month/year) to allow this information to appear in search results | To do | 2 | Thengo and Joel | 2017-02-01 | 2017-02-25
| Ensure search results can be organized in chronological order (newest to oldest), and include tags | To do | 2 | Joel
Most Read | Using WordPress reporting, pull a listing of the Top 5 articles read (most popular) in the previous quarter (based on page views). Post on the website. | To do | 1 | Thengo | 2017-02-15 | 2017-02-25
| Integrate into journal home page updates the updating of this listing of papers | To do | ongoing | Thengo
FUTURE REDESIGN
Jayne Dawkins | Consider redesign of article PDF, perhaps for 2018, to provide more visual interest and target certain article sections to a specific look and feel | To do | 2018 | All
| These are information pages on the site, not part of the issue dataset | To do | 2018 | All
USAGE and SEO
Analytics | Identify system and reports to be pulled on a monthly basis to measure impact and establish trends | To do | 1 | Andrew | 2017-02-05
| Identify team member who will be responsible to generate reports | Done |  | Andrew | Done
| Reports would be part of regular reporting to the Ed Board and AJPP | To do | 1 | Andrew | 2017-02-05 |  | Next board meeting 24-Feb-17
SEO | Use author email list and others who have signed up for alerts to ask all to link to MMJ | To do | 2 or 3 based on Volunteer timing | Jayne
| Have webmaster review the site architecture to ensure there is no obstacle to search engines crawling the site | To do | 1 | Joel
| Review pages to see where "cross linking" is possible (from one MMJ page to another, e.g., About Us pages should provide links to the other info pages) | To do | 1 | All
MMJ on AJOL
| Ensure all updates are made to MMJ pages on AJOL | Done |  | Thengo
| Explore possibility of uploading MMJ content directly to AJOL; pilot to determine time and resources vs value | To do | 1 | Thengo
SOCIAL MEDIA
Jayne Dawkins | Identify current social media properties: Facebook and Twitter | Done
| Identify how each will be used to the journal benefit |  | 2 or 3 based on Volunteer timing
Identify resource for updating each social media page
| Update the MMJ graphic so it fits the social media header | To do |  | Andrew
Follow guidance stated above to improve linking and connections.
| Determine connection for Journal club between MMJ site and social media | To do | 2 | All
| Follow social media activity to see impact on journal usage to repeat this |  | 2
PROMOTION AND MARKETING
Branding | Follow guidance stated above to improve linking and connections. Next volunteer will take this on and help develop social media strategy as well. |  | 2 or 3 based on Volunteer timing
Alerts and Campaigns
Connections
Ads
VOLUNTEER ACTIONS
| Weekly recap on progress | Done for 1 and 2; to do for week #3 |  | CBC |  | 2017-02-08
| Project wrap-up and next steps, to ensure transition to next volunteer. Document road map and phased implementation | To do | NA | CBC |  | 2017-02-08
| Assist Editor in Chief as requested with May AJPP presentation | Ongoing
| Provide volunteer evaluation form for team completion | To do | 1 | CBC |  | 2017-02-08
t